## Duration Worksheet
Duration Estimating Worksheet
Project Title: | SweetSpot |  |  | Date Prepared:
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate | Class Days to Complete | Comments | Assigned To
|  |  |  | (o + 4e + p)/6 |  |  |  |  | Team Member Name |  | Team Member Name
Create Employee Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create JobPosition Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Location Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Model Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Brand Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Clothing Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Accessories Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create TradeIn Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Layaway Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Accounts Receivable Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create TaxRate Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Orders Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Transfers Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Returns Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create OnHold Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Quick Sale - Grab Guest Cust | 0.2 | 0.5 | 1 | 0.53333 | 0 | 0.53333 | 0.26667 |  |  | 0 |  | 0
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Multi-Threading for each login | 2 | 4 | 8 | 4.3333 | 0 | 4.3333 | 2.1667 |  |  | 0 |  | 0
Click MOP enter amount | 3 | 4.5 | 8 | 4.8333 | 0 | 4.8333 | 2.4167 |  |  | 0 |  | 0
Customer - direct access to start sale | 1 | 3 | 5 | 3 | 0 | 3 | 1.5 |  |  | 0 |  | 0
If Guest no Layaway | 0.5 | 1 | 2 | 1.0833 | 0 | 1.0833 | 0.54167 |  |  | 0 |  | 0
Login at Home Page | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
After Sale is processed go home auto logout | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
If password only for login - search userInfo for username, location | 2 | 4 | 6 | 4 | 0 | 4 | 2 |  |  | 0 |  | 0
Create userInfo Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Inventory search by Item Type - Dropdown | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Dropdown list for models & brands based on Type | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
New Item Button for adding Items | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Trade in (-) and only subtract from sub-total | 2 | 2.5 | 4 | 2.6667 | 0 | 2.6667 | 1.3333 |  |  | 0 |  | 0
Sale, all Header buttons disabled | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Draw Sales Designs | 2 | 2.5 | 3 | 2.5 | 0 | 2.5 | 1.25 |  |  | 0 |  | 0
Better define JobRoles for Security | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Create Employee Class | 3 | 5 | 7 | 5 | 0 | 5 | 2.5 |  |  | 0 |  | 0
Starighten DLL, remove duplicate code, more robusty | 2 | 4 | 6 | 4 | 0 | 4 | 2 |  |  | 0 |  | 0
Add transfer to Sales | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 |  |  | 0 |  | 0
Transfer like cart but no totals | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Transfer - Select location to send to | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Taxes- Dropdown for country | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Employee - username password, change password, security question | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Settings - Taxes | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Reports - Daily Sales | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Setting - Employee | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Settings - Bulk Excel Loads | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Reports - Cash out | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
New Employee button for adding Employee | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New Customer button for adding customer | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New Add Item Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New Add Customer Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New add Employee Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
Bulk load functionality for items | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
Bulk load functionality for customers | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
Bulk load functionality for employees | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
[10 empty] | 0 |  | 0
[5 empty] | Total Estimate | 83.1 | 41.55 |  | 0 | 0 | 0 | 0
[5 empty] | Time Budget | 0
[5 empty] | Slack Time | -83.1 |  |  |  | 0 |  | 0

## Nathan
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration
Create Employee Table | 0.1 | 0.2 | 0.5
Create JobPosition Table | 0.1 | 0.2 | 0.5
Create Location Table | 0.1 | 0.2 | 0.5
Create Model Table | 0.1 | 0.2 | 0.5
Create Brand Table | 0.1 | 0.2 | 0.5
Create Clothing Table | 0.1 | 0.2 | 0.5
Create Accessories Table | 0.1 | 0.2 | 0.5
Create TradeIn Table | 0.1 | 0.2 | 0.5
Create Layaway Table | 0.1 | 0.2 | 0.5
Create Accounts Receivable Table | 0.1 | 0.2 | 0.5
Create TaxRate Table | 0.1 | 0.2 | 0.5
Create Orders Table | 0.1 | 0.2 | 0.5
Create Transfers Table | 0.1 | 0.2 | 0.5
Create Returns Table | 0.1 | 0.2 | 0.5
Create OnHold Table | 0.1 | 0.2 | 0.5
Quick Sale - Grab Guest Cust | 0.2 | 0.5 | 1
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1 | 1.5
Multi-Threading for each login | 2 | 4 | 8
Click MOP enter amount | 3 | 4.5 | 8
Customer - direct access to start sale | 1 | 3 | 5
If Guest no Layaway | 0.5 | 1 | 2
Login at Home Page | 3 | 4 | 6
After Sale is processed go home auto logout | 1 | 1.5 | 3
If password only for login - search userInfo for username, location | 2 | 4 | 6
Create userInfo Table | 0.1 | 0.2 | 0.5
Inventory search by Item Type - Dropdown | 1 | 1.5 | 3
Dropdown list for models & brands based on Type | 1 | 1.5 | 3
New Item Button for adding Items | 1 | 2 | 3
Trade in (-) and only subtract from sub-total | 2 | 2.5 | 4
Sale, all Header buttons disabled | 1 | 2 | 3
Draw Sales Designs | 2 | 2.5 | 3
Better define JobRoles for Security | 0.5 | 1 | 1.5
Create Employee Class | 3 | 5 | 7
Starighten DLL, remove duplicate code, more robusty | 2 | 4 | 6
Add transfer to Sales | 0.5 | 1 | 3
Transfer like cart but no totals | 1 | 1.5 | 3
Transfer - Select location to send to | 1 | 1.5 | 3
Taxes- Dropdown for country | 0.5 | 1 | 1.5
Employee - username password, change password, security question | 1 | 1.5 | 3
Settings - Taxes | 0.5 | 1 | 1.5
Reports - Daily Sales | 0.5 | 1 | 1.5
Setting - Employee | 0.5 | 1 | 1.5
Settings - Bulk Excel Loads | 0.5 | 1 | 1.5
Reports - Cash out | 0.5 | 1 | 1.5
New Employee button for adding Employee | 1 | 1.5 | 2
New Customer button for adding customer | 1 | 1.5 | 2
New Add Item Page | 1 | 1.5 | 2
New Add Customer Page | 1 | 1.5 | 2
New add Employee Page | 1 | 1.5 | 2
Bulk load functionality for items | 3 | 4 | 6
Bulk load functionality for customers | 3 | 4 | 6
Bulk load functionality for employees | 3 | 4 | 6

## Tyler
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration
Create Employee Table | 0.5 | 1 | 3
Create JobPosition Table | 0.5 | 1 | 3
Create Location Table | 0.5 | 1 | 3
Create Model Table | 0.5 | 1 | 3
Create Brand Table | 0.5 | 1 | 3
Create Clothing Table | 0.5 | 1 | 3
Create Accessories Table | 0.5 | 1 | 3
Create TradeIn Table | 0.5 | 1 | 3
Create Layaway Table | 0.5 | 1 | 3
Create Accounts Receivable Table | 0.5 | 1 | 3
Create TaxRate Table | 0.5 | 1 | 3
Create Orders Table | 0.5 | 1 | 3
Create Transfers Table | 0.5 | 1 | 3
Create Returns Table | 0.5 | 1 | 3
Create OnHold Table | 0.5 | 1 | 3
Quick Sale - Grab Guest Cust | 0.5 | 1 | 3
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1.5 | 3
Multi-Threading for each login | 3 | 6 | 9
Click MOP enter amount | 1 | 3 | 5
Customer - direct access to start sale | 0.5 | 1.5 | 4
If Guest no Layaway | 0.1 | 0.3 | 1.5
Login at Home Page | 1 | 2 | 6
After Sale is processed go home auto logout | 1 | 2 | 6
If password only for login - search userInfo for username, location | 1 | 2 | 6
Create userInfo Table | 0.5 | 1 | 3
Inventory search by Item Type - Dropdown | 1 | 2 | 4
Dropdown list for models & brands based on Type | 0.2 | 1 | 1.5
New Item Button for adding Items | 1 | 1.5 | 3
Trade in (-) and only subtract from sub-total | 0.2 | 0.5 | 2
Sale, all Header buttons disabled | 0.1 | 0.5 | 1
Draw Sales Designs | 0.3 | 1 | 1.5
Better define JobRoles for Security | 0.2 | 0.5 | 1
Create Employee Class | 2 | 3 | 5
Starighten DLL, remove duplicate code, more robusty | 1 | 2.5 | 4
Add transfer to Sales | 0.5 | 1 | 2.5
Transfer like cart but no totals | 0.5 | 1 | 2.5
Transfer - Select location to send to | 0.5 | 1 | 2.5
Taxes- Dropdown for country | 0.2 | 0.5 | 1
Employee - username password, change password, security question | 1 | 2 | 3
Settings - Taxes | 0.2 | 0.5 | 1
Reports - Daily Sales | 1 | 1.5 | 2.5
Setting - Employee | 0.2 | 0.5 | 1
Settings - Bulk Excel Loads | 3 | 4 | 6
Reports - Cash out | 1 | 2 | 3
New Employee button for adding Employee | 1 | 1.5 | 2
New Customer button for adding customer | 1 | 1.5 | 2
New Add Item Page | 1 | 1.5 | 2
New Add Customer Page | 1 | 1.5 | 2
New add Employee Page | 1 | 1.5 | 2
Bulk load functionality for items | 2 | 3 | 6
Bulk load functionality for customers | 2 | 3 | 6
Bulk load functionality for employees | 2 | 3 | 6

## Final
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate
Create Employee Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create JobPosition Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Location Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Model Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Brand Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Clothing Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Accessories Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create TradeIn Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Layaway Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Accounts Receivable Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create TaxRate Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Orders Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Transfers Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create Returns Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Create OnHold Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Quick Sale - Grab Guest Cust | 0.35 | 0.75 | 2 | 0.89167 | 0 | 0.89167
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1.25 | 2.25 | 1.2917 | 0 | 1.2917
Multi-Threading for each login | 2.5 | 5 | 8.5 | 5.1667 | 0 | 5.1667
Click MOP enter amount | 2 | 3.75 | 6.5 | 3.9167 | 0 | 3.9167
Customer - direct access to start sale | 0.75 | 2.25 | 4.5 | 2.375 | 0 | 2.375
If Guest no Layaway | 0.3 | 0.65 | 1.75 | 0.775 | 0 | 0.775
Login at Home Page | 2 | 3 | 6 | 3.3333 | 0 | 3.3333
After Sale is processed go home auto logout | 1 | 1.75 | 4.5 | 2.0833 | 0 | 2.0833
If password only for login - search userInfo for username, location | 1.5 | 3 | 6 | 3.25 | 0 | 3.25
Create userInfo Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167
Inventory search by Item Type - Dropdown | 1 | 1.75 | 3.5 | 1.9167 | 0 | 1.9167
Dropdown list for models & brands based on Type | 0.6 | 1.25 | 2.25 | 1.3083 | 0 | 1.3083
New Item Button for adding Items | 1 | 1.75 | 3 | 1.8333 | 0 | 1.8333
Trade in (-) and only subtract from sub-total | 1.1 | 1.5 | 3 | 1.6833 | 0 | 1.6833
Sale, all Header buttons disabled | 0.55 | 1.25 | 2 | 1.2583 | 0 | 1.2583
Draw Sales Designs | 1.15 | 1.75 | 2.25 | 1.7333 | 0 | 1.7333
Better define JobRoles for Security | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667
Create Employee Class | 2.5 | 4 | 6 | 4.0833 | 0 | 4.0833
Starighten DLL, remove duplicate code, more robusty | 1.5 | 3.25 | 5 | 3.25 | 0 | 3.25
Add transfer to Sales | 0.5 | 1 | 2.75 | 1.2083 | 0 | 1.2083
Transfer like cart but no totals | 0.75 | 1.25 | 2.75 | 1.4167 | 0 | 1.4167
Transfer - Select location to send to | 0.75 | 1.25 | 2.75 | 1.4167 | 0 | 1.4167
Taxes- Dropdown for country | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667
Employee - username password, change password, security question | 1 | 1.75 | 3 | 1.8333 | 0 | 1.8333
Settings - Taxes | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667
Reports - Daily Sales | 0.75 | 1.25 | 2 | 1.2917 | 0 | 1.2917
Setting - Employee | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667
Settings - Bulk Excel Loads | 1.75 | 2.5 | 3.75 | 2.5833 | 0 | 2.5833
Reports - Cash out | 0.75 | 1.5 | 2.25 | 1.5 | 0 | 1.5
New Employee button for adding Employee | 1 | 1.5 | 2 | 1.5 | 0 | 1.5
New Customer button for adding customer | 1 | 1.5 | 2 | 1.5 | 0 | 1.5
New Add Item Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5
New Add Customer Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5
New add Employee Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5
Bulk load functionality for items | 2.5 | 3.5 | 6 | 3.75 | 0 | 3.75
Bulk load functionality for customers | 2.5 | 3.5 | 6 | 3.75 | 0 | 3.75
Bulk load functionality for employees | 2.5 | 3.5 | 6 | 3.75 | 0 | 3.75