## Duration Worksheet
Duration Estimating Worksheet
Project Title: | SweetSpot |  |  | Date Prepared:
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate | Class Days to Complete | Comments | Assigned To
|  |  |  | (o + 4e + p)/6 |  |  |  |  | Team Member Name |  | Team Member Name
Create Employee Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create JobPosition Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Location Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Model Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Brand Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Clothing Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Accessories Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create TradeIn Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Layaway Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Accounts Receivable Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create TaxRate Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Orders Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Transfers Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create Returns Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Create OnHold Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Quick Sale - Grab Guest Cust | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 |  |  | 0 |  | 0
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1.5 | 3 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Multi-Threading for each login | 3 | 6 | 9 | 6 | 0 | 6 | 3 |  |  | 0 |  | 0
Click MOP enter amount | 1 | 3 | 5 | 3 | 0 | 3 | 1.5 |  |  | 0 |  | 0
Customer - direct access to start sale | 0.5 | 1.5 | 4 | 1.75 | 0 | 1.75 | 0.875 |  |  | 0 |  | 0
If Guest no Layaway | 0.1 | 0.3 | 1.5 | 0.46667 | 0 | 0.46667 | 0.23333 |  |  | 0 |  | 0
Login at Home Page | 1 | 2 | 6 | 2.5 | 0 | 2.5 | 1.25 |  |  | 0 |  | 0
After Sale is processed go home auto logout | 1 | 2 | 6 | 2.5 | 0 | 2.5 | 1.25 |  |  | 0 |  | 0
If password only for login - search userInfo for username, location | 1 | 2 | 6 | 2.5 | 0 | 2.5 | 1.25 | Database |  | 0 |  | #VALUE!
Create userInfo Table | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 | Database |  | 0 |  | #VALUE!
Inventory search by Item Type - Dropdown | 1 | 2 | 4 | 2.1667 | 0 | 2.1667 | 1.0833 | Database |  | 0 |  | #VALUE!
Dropdown list for models & brands based on Type | 0.2 | 1 | 1.5 | 0.95 | 0 | 0.95 | 0.475 | Database |  | 0 |  | #VALUE!
New Item Button for adding Items | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 | Database |  | 0 |  | #VALUE!
Trade in (-) and only subtract from sub-total | 0.2 | 0.5 | 2 | 0.7 | 0 | 0.7 | 0.35 |  |  | 0 |  | 0
Sale, all Header buttons disabled | 0.1 | 0.5 | 1 | 0.51667 | 0 | 0.51667 | 0.25833 |  |  | 0 |  | 0
Draw Sales Designs | 0.3 | 1 | 1.5 | 0.96667 | 0 | 0.96667 | 0.48333 |  |  | 0 |  | 0
Better define JobRoles for Security | 0.2 | 0.5 | 1 | 0.53333 | 0 | 0.53333 | 0.26667 |  |  | 0 |  | 0
Create Employee Class | 2 | 3 | 5 | 3.1667 | 0 | 3.1667 | 1.5833 |  |  | 0 |  | 0
Starighten DLL, remove duplicate code, more robusty | 1 | 2.5 | 4 | 2.5 | 0 | 2.5 | 1.25 |  |  | 0 |  | 0
Add transfer to Sales | 0.5 | 1 | 2.5 | 1.1667 | 0 | 1.1667 | 0.58333 |  |  | 0 |  | 0
Transfer like cart but no totals | 0.5 | 1 | 2.5 | 1.1667 | 0 | 1.1667 | 0.58333 |  |  | 0 |  | 0
Transfer - Select location to send to | 0.5 | 1 | 2.5 | 1.1667 | 0 | 1.1667 | 0.58333 |  |  | 0 |  | 0
Taxes- Dropdown for country | 0.2 | 0.5 | 1 | 0.53333 | 0 | 0.53333 | 0.26667 |  |  | 0 |  | 0
Employee - username password, change password, security question | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Settings - Taxes | 0.2 | 0.5 | 1 | 0.53333 | 0 | 0.53333 | 0.26667 |  |  | 0 |  | 0
Reports - Daily Sales | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Setting - Employee | 0.2 | 0.5 | 1 | 0.53333 | 0 | 0.53333 | 0.26667 |  |  | 0 |  | 0
Settings - Bulk Excel Loads | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
Reports - Cash out | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
| 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
| 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
| 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
| 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
| 2 | 3 | 6 | 3.3333 | 0 | 3.3333 | 1.6667 |  |  | 0 |  | 0
| 2 | 3 | 6 | 3.3333 | 0 | 3.3333 | 1.6667 |  |  | 0 |  | 0
| 2 | 3 | 6 | 3.3333 | 0 | 3.3333 | 1.6667 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
[10 empty] | 0 |  | 0
[5 empty] | Total Estimate | 85.5667 | 42.7833 |  | 0 | 0 | 0 | #VALUE!
[5 empty] | Time Budget | 0
[5 empty] | Slack Time | -85.5667 |  |  |  | 0 |  | #VALUE!