## Duration Worksheet
Duration Estimating Worksheet
Project Title: | SweetSpot |  |  | Date Prepared:
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate | Class Days to Complete | Comments | Assigned To
|  |  |  | (o + 4e + p)/6 |  |  |  |  | Team Member Name |  | Team Member Name
Create Employee Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create JobPosition Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Location Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Model Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Brand Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Clothing Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Accessories Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create TradeIn Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Layaway Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Accounts Receivable Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create TaxRate Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Orders Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Transfers Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create Returns Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Create OnHold Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Quick Sale - Grab Guest Cust | 0.2 | 0.5 | 1 | 0.53333 | 0 | 0.53333 | 0.26667 |  |  | 0 |  | 0
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Multi-Threading for each login | 2 | 4 | 8 | 4.3333 | 0 | 4.3333 | 2.1667 |  |  | 0 |  | 0
Click MOP enter amount | 3 | 4.5 | 8 | 4.8333 | 0 | 4.8333 | 2.4167 |  |  | 0 |  | 0
Customer - direct access to start sale | 1 | 3 | 5 | 3 | 0 | 3 | 1.5 |  |  | 0 |  | 0
If Guest no Layaway | 0.5 | 1 | 2 | 1.0833 | 0 | 1.0833 | 0.54167 |  |  | 0 |  | 0
Login at Home Page | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
After Sale is processed go home auto logout | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
If password only for login - search userInfo for username, location | 2 | 4 | 6 | 4 | 0 | 4 | 2 |  |  | 0 |  | 0
Create userInfo Table | 0.1 | 0.2 | 0.5 | 0.23333 | 0 | 0.23333 | 0.11667 |  |  | 0 |  | 0
Inventory search by Item Type - Dropdown | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Dropdown list for models & brands based on Type | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
New Item Button for adding Items | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Trade in (-) and only subtract from sub-total | 2 | 2.5 | 4 | 2.6667 | 0 | 2.6667 | 1.3333 |  |  | 0 |  | 0
Sale, all Header buttons disabled | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Draw Sales Designs | 2 | 2.5 | 3 | 2.5 | 0 | 2.5 | 1.25 |  |  | 0 |  | 0
Better define JobRoles for Security | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Create Employee Class | 3 | 5 | 7 | 5 | 0 | 5 | 2.5 |  |  | 0 |  | 0
Starighten DLL, remove duplicate code, more robusty | 2 | 4 | 6 | 4 | 0 | 4 | 2 |  |  | 0 |  | 0
Add transfer to Sales | 0.5 | 1 | 3 | 1.25 | 0 | 1.25 | 0.625 |  |  | 0 |  | 0
Transfer like cart but no totals | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Transfer - Select location to send to | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Taxes- Dropdown for country | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Employee - username password, change password, security question | 1 | 1.5 | 3 | 1.6667 | 0 | 1.6667 | 0.83333 |  |  | 0 |  | 0
Settings - Taxes | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Reports - Daily Sales | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Setting - Employee | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Settings - Bulk Excel Loads | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
Reports - Cash out | 0.5 | 1 | 1.5 | 1 | 0 | 1 | 0.5 |  |  | 0 |  | 0
New Employee button for adding Employee | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New Customer button for adding customer | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New Add Item Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New Add Customer Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
New add Employee Page | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
Bulk load functionality for items | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
Bulk load functionality for customers | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
Bulk load functionality for employees | 3 | 4 | 6 | 4.1667 | 0 | 4.1667 | 2.0833 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
[10 empty] | 0 |  | 0
[5 empty] | Total Estimate | 83.1 | 41.55 |  | 0 | 0 | 0 | 0
[5 empty] | Time Budget | 0
[5 empty] | Slack Time | -83.1 |  |  |  | 0 |  | 0

## Nathan
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration
Create Employee Table | 0.1 | 0.2 | 0.5
Create JobPosition Table | 0.1 | 0.2 | 0.5
Create Location Table | 0.1 | 0.2 | 0.5
Create Model Table | 0.1 | 0.2 | 0.5
Create Brand Table | 0.1 | 0.2 | 0.5
Create Clothing Table | 0.1 | 0.2 | 0.5
Create Accessories Table | 0.1 | 0.2 | 0.5
Create TradeIn Table | 0.1 | 0.2 | 0.5
Create Layaway Table | 0.1 | 0.2 | 0.5
Create Accounts Receivable Table | 0.1 | 0.2 | 0.5
Create TaxRate Table | 0.1 | 0.2 | 0.5
Create Orders Table | 0.1 | 0.2 | 0.5
Create Transfers Table | 0.1 | 0.2 | 0.5
Create Returns Table | 0.1 | 0.2 | 0.5
Create OnHold Table | 0.1 | 0.2 | 0.5
Quick Sale - Grab Guest Cust | 0.2 | 0.5 | 1
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.5 | 1 | 1.5
Multi-Threading for each login | 2 | 4 | 8
Click MOP enter amount | 3 | 4.5 | 8
Customer - direct access to start sale | 1 | 3 | 5
If Guest no Layaway | 0.5 | 1 | 2
Login at Home Page | 3 | 4 | 6
After Sale is processed go home auto logout | 1 | 1.5 | 3
If password only for login - search userInfo for username, location | 2 | 4 | 6
Create userInfo Table | 0.1 | 0.2 | 0.5
Inventory search by Item Type - Dropdown | 1 | 1.5 | 3
Dropdown list for models & brands based on Type | 1 | 1.5 | 3
New Item Button for adding Items | 1 | 2 | 3
Trade in (-) and only subtract from sub-total | 2 | 2.5 | 4
Sale, all Header buttons disabled | 1 | 2 | 3
Draw Sales Designs | 2 | 2.5 | 3
Better define JobRoles for Security | 0.5 | 1 | 1.5
Create Employee Class | 3 | 5 | 7
Starighten DLL, remove duplicate code, more robusty | 2 | 4 | 6
Add transfer to Sales | 0.5 | 1 | 3
Transfer like cart but no totals | 1 | 1.5 | 3
Transfer - Select location to send to | 1 | 1.5 | 3
Taxes- Dropdown for country | 0.5 | 1 | 1.5
Employee - username password, change password, security question | 1 | 1.5 | 3
Settings - Taxes | 0.5 | 1 | 1.5
Reports - Daily Sales | 0.5 | 1 | 1.5
Setting - Employee | 0.5 | 1 | 1.5
Settings - Bulk Excel Loads | 0.5 | 1 | 1.5
Reports - Cash out | 0.5 | 1 | 1.5
New Employee button for adding Employee | 1 | 1.5 | 2
New Customer button for adding customer | 1 | 1.5 | 2
New Add Item Page | 1 | 1.5 | 2
New Add Customer Page | 1 | 1.5 | 2
New add Employee Page | 1 | 1.5 | 2
Bulk load functionality for items | 3 | 4 | 6
Bulk load functionality for customers | 3 | 4 | 6
Bulk load functionality for employees | 3 | 4 | 6

## Tyler
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration
Create Employee Table
Create JobPosition Table
Create Location Table
Create Model Table
Create Brand Table
Create Clothing Table
Create Accessories Table
Create TradeIn Table
Create Layaway Table
Create Accounts Receivable Table
Create TaxRate Table
Create Orders Table
Create Transfers Table
Create Returns Table
Create OnHold Table
Quick Sale - Grab Guest Cust
Function - When adding Item to sale, "If used and < $300, remove PST"
Multi-Threading for each login
Click MOP enter amount
Customer - direct access to start sale
If Guest no Layaway
Login at Home Page
After Sale is processed go home auto logout
If password only for login - search userInfo for username, location
Create userInfo Table
Inventory search by Item Type - Dropdown
Dropdown list for models & brands based on Type
New Item Button for adding Items
Trade in (-) and only subtract from sub-total
Sale, all Header buttons disabled
Draw Sales Designs
Better define JobRoles for Security
Create Employee Class
Starighten DLL, remove duplicate code, more robusty
Add transfer to Sales
Transfer like cart but no totals
Transfer - Select location to send to
Taxes- Dropdown for country
Employee - username password, change password, security question
Settings - Taxes
Reports - Daily Sales
Setting - Employee
Settings - Bulk Excel Loads
Reports - Cash out
New Employee button for adding Employee
New Customer button for adding customer
New Add Item Page
New Add Customer Page
New add Employee Page
Bulk load functionality for items
Bulk load functionality for customers
Bulk load functionality for employees

## Final
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate
Create Employee Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.23333
Create JobPosition Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Location Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Model Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Brand Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Clothing Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Accessories Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create TradeIn Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Layaway Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Accounts Receivable Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create TaxRate Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Orders Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Transfers Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create Returns Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Create OnHold Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Quick Sale - Grab Guest Cust | 0.1 | 0.25 | 0.5 | 0.26667 | 0 | 0.26667
Function - When adding Item to sale, "If used and < $300, remove PST" | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Multi-Threading for each login | 1 | 2 | 4 | 2.1667 | 0 | 2.1667
Click MOP enter amount | 1.5 | 2.25 | 4 | 2.4167 | 0 | 2.4167
Customer - direct access to start sale | 0.5 | 1.5 | 2.5 | 1.5 | 0 | 1.5
If Guest no Layaway | 0.25 | 0.5 | 1 | 0.54167 | 0 | 0.54167
Login at Home Page | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833
After Sale is processed go home auto logout | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333
If password only for login - search userInfo for username, location | 1 | 2 | 3 | 2 | 0 | 2
Create userInfo Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667
Inventory search by Item Type - Dropdown | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333
Dropdown list for models & brands based on Type | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333
New Item Button for adding Items | 0.5 | 1 | 1.5 | 1 | 0 | 1
Trade in (-) and only subtract from sub-total | 1 | 1.25 | 2 | 1.3333 | 0 | 1.3333
Sale, all Header buttons disabled | 0.5 | 1 | 1.5 | 1 | 0 | 1
Draw Sales Designs | 1 | 1.25 | 1.5 | 1.25 | 0 | 1.25
Better define JobRoles for Security | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Create Employee Class | 1.5 | 2.5 | 3.5 | 2.5 | 0 | 2.5
Starighten DLL, remove duplicate code, more robusty | 1 | 2 | 3 | 2 | 0 | 2
Add transfer to Sales | 0.25 | 0.5 | 1.5 | 0.625 | 0 | 0.625
Transfer like cart but no totals | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333
Transfer - Select location to send to | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333
Taxes- Dropdown for country | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Employee - username password, change password, security question | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333
Settings - Taxes | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Reports - Daily Sales | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Setting - Employee | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Settings - Bulk Excel Loads | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
Reports - Cash out | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5
New Employee button for adding Employee | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75
New Customer button for adding customer | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75
New Add Item Page | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75
New Add Customer Page | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75
New add Employee Page | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75
Bulk load functionality for items | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833
Bulk load functionality for customers | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833
Bulk load functionality for employees | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833