## Duration Worksheet
Duration Estimating Worksheet
Project Title: | SweetSpot |  |  | Date Prepared:
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration | Weighted Duration | Reserve Analysis (Optional, requires comment) | Final Estimate | Class Days to Complete | Comments | Assigned To
|  |  |  | (o + 4e + p)/6 |  |  |  |  | Team Member Name |  | Team Member Name
Add Table - Accessories Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Accounts Receivable Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Brands Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Clothing Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Employees Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Item Table to Club Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667 | 0.058333 |  |  | 0 |  | 0
Add Table - Job Position Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Layaway Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Location Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Model Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - On Hold Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Orders Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Returns Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Tax Rate Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Trade Ins Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - Transfers Table | 0.3 | 0.6 | 1.75 | 0.74167 | 0 | 0.74167 | 0.37083 |  |  | 0 |  | 0
Add Table - User Info Table | 0.05 | 0.1 | 0.25 | 0.11667 | 0 | 0.11667 | 0.058333 |  |  | 0 |  | 0
Change Requests | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333 | 0.41667 |  |  | 0 |  | 0
Client Meetings | 2.5 | 4 | 8 | 4.4167 | 0 | 4.4167 | 2.2083 |  |  | 0 |  | 0
Define Job Roles | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667 | 0.38333 |  |  | 0 |  | 0
Estimates | 0.5 | 1.25 | 1.5 | 1.1667 | 0 | 1.1667 | 0.58333 |  |  | 0 |  | 0
Final Report | 2 | 3 | 4 | 3 | 0 | 3 | 1.5 |  |  | 0 |  | 0
Functionality - Add Customer On Sale | 0.75 | 1.25 | 2 | 1.2917 | 0 | 1.2917 | 0.64583 |  |  | 0 |  | 0
Functionality - Add Item to Sale | 0.75 | 1.25 | 2 | 1.2917 | 0 | 1.2917 | 0.64583 |  |  | 0 |  | 0
Functionality - Adding used item, if < $300 remove PST | 0.5 | 1.25 | 2.25 | 1.2917 | 0 | 1.2917 | 0.64583 |  |  | 0 |  | 0
Functionality - Bulk Load for Customers | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833 | 1.0417 |  |  | 0 |  | 0
Functionality - Bulk Load for Employees | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833 | 1.0417 |  |  | 0 |  | 0
Functionality - Bulk Load for Items | 1.5 | 2 | 3 | 2.0833 | 0 | 2.0833 | 1.0417 |  |  | 0 |  | 0
Functionality - Cancel Sale | 0.75 | 1.25 | 2 | 1.2917 | 0 | 1.2917 | 0.64583 |  |  | 0 |  | 0
Functionality - Checkout Calculate Balance | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Checkout Calculate GST | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Checkout Calculate On Sale Total | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Checkout Calculate PST | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Checkout Calculate Subtotal | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Checkout Calculate Total Owing | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Checkout Calculate Trade In Total | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Create Employee Class | 2.5 | 4 | 6 | 4.0833 | 0 | 4.0833 | 2.0417 |  |  | 0 |  | 0
Functionality - Create Threaded Current User Class | 1.5 | 2.5 | 4 | 2.5833 | 0 | 2.5833 | 1.2917 |  |  | 0 |  | 0
Functionality - Dropdown for In Store Sale or Shipping | 0.5 | 0.75 | 1.5 | 0.83333 | 0 | 0.83333 | 0.41667 |  |  | 0 |  | 0
Functionality - During Sale, all Header button disabled | 0.55 | 1.25 | 2 | 1.2583 | 0 | 1.2583 | 0.62917 |  |  | 0 |  | 0
Functionality - Edit Customer | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - Edit Employee | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - Edit Item | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - From selected Customer, ability to Start Sale | 0.75 | 2.25 | 4.5 | 2.375 | 0 | 2.375 | 1.1875 |  |  | 0 |  | 0
Functionality - Generic Trade In Sku | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Functionality - If Customer is Guest, no Layaway Option | 0.3 | 0.65 | 1.75 | 0.775 | 0 | 0.775 | 0.3875 |  |  | 0 |  | 0
Functionality - Inventory Search | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Inventory Search by Type | 1 | 1.75 | 3.5 | 1.9167 | 0 | 1.9167 | 0.95833 |  |  | 0 |  | 0
Functionality - Make DLL more robust | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Functionality - Multi Threading for each Login | 2.5 | 5 | 8.5 | 5.1667 | 0 | 5.1667 | 2.5833 |  |  | 0 |  | 0
Functionality - New Customer button | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - New Employee button | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - New Item button | 1 | 1.75 | 3 | 1.8333 | 0 | 1.8333 | 0.91667 |  |  | 0 |  | 0
Functionality - Password only Login | 1.5 | 3 | 6 | 3.25 | 0 | 3.25 | 1.625 |  |  | 0 |  | 0
Functionality - Proceed To Checkout | 0.25 | 0.5 | 0.75 | 0.5 | 0 | 0.5 | 0.25 |  |  | 0 |  | 0
Functionality - Quick Sale, grab Guest Customer | 0.35 | 0.75 | 2 | 0.89167 | 0 | 0.89167 | 0.44583 |  |  | 0 |  | 0
Functionality - Remove duplicate code in DLL | 0.5 | 1 | 2 | 1.0833 | 0 | 1.0833 | 0.54167 |  |  | 0 |  | 0
Functionality - Remove Item From Cart | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - Roll Over Cost | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - Sale is processed, go home | 1 | 1.75 | 4.5 | 2.0833 | 0 | 2.0833 | 1.0417 |  |  | 0 |  | 0
Functionality - Select Method of Payment, enter amount | 2 | 3.75 | 6.5 | 3.9167 | 0 | 3.9167 | 1.9583 |  |  | 0 |  | 0
Functionality - Trade Ins (-) remove from Subtotal | 1.1 | 1.5 | 3 | 1.6833 | 0 | 1.6833 | 0.84167 |  |  | 0 |  | 0
Functionality - Trade Ins Popup | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Functionality - Trade Ins see Cost not Price | 0.25 | 0.75 | 1.5 | 0.79167 | 0 | 0.79167 | 0.39583 |  |  | 0 |  | 0
Learning current application | 5 | 7.5 | 10 | 7.5 | 0 | 7.5 | 3.75 |  |  | 0 |  | 0
Meeting Transciption | 1 | 1.25 | 2 | 1.3333 | 0 | 1.3333 | 0.66667 |  |  | 0 |  | 0
Planning Meeting | 2.5 | 4 | 7.5 | 4.3333 | 0 | 4.3333 | 2.1667 |  |  | 0 |  | 0
Project Proposal | 2 | 3 | 4 | 3 | 0 | 3 | 1.5 |  |  | 0 |  | 0
QA | 5 | 7.5 | 12.5 | 7.9167 | 0 | 7.9167 | 3.9583 |  |  | 0 |  | 0
Research | 1.5 | 2.5 | 4 | 2.5833 | 0 | 2.5833 | 1.2917 |  |  | 0 |  | 0
Review Transmittal Documentation | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Screens - Draw Sales Layout Designs | 1.15 | 1.75 | 2.25 | 1.7333 | 0 | 1.7333 | 0.86667 |  |  | 0 |  | 0
Screens - Employees > more fields | 1 | 1.75 | 3 | 1.8333 | 0 | 1.8333 | 0.91667 |  |  | 0 |  | 0
Screens - Initial Redesign | 0.5 | 1.5 | 2 | 1.4167 | 0 | 1.4167 | 0.70833 |  |  | 0 |  | 0
Screens - Login at home page | 2 | 3 | 6 | 3.3333 | 0 | 3.3333 | 1.6667 |  |  | 0 |  | 0
Screens - Master Page | 0.75 | 1.5 | 2.5 | 1.5417 | 0 | 1.5417 | 0.77083 |  |  | 0 |  | 0
Screens - New Add Customer page | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Screens - New Add Employee page | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Screens - New Add Item page | 0.5 | 0.75 | 1 | 0.75 | 0 | 0.75 | 0.375 |  |  | 0 |  | 0
Screens - Reports > Cash Out | 0.75 | 1.5 | 2.25 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
Screens - Reports > Daily Sales | 0.75 | 1.25 | 2 | 1.2917 | 0 | 1.2917 | 0.64583 |  |  | 0 |  | 0
Screens - Sales > Transfers | 0.5 | 1 | 2.75 | 1.2083 | 0 | 1.2083 | 0.60417 |  |  | 0 |  | 0
Screens - Sales Cart | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Screens - Sales Checkout | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Screens - Settings > Bulk Excel Loads | 1.75 | 2.5 | 3.75 | 2.5833 | 0 | 2.5833 | 1.2917 |  |  | 0 |  | 0
Screens - Settings > Employees | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667 | 0.38333 |  |  | 0 |  | 0
Screens - Settings > Taxes | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667 | 0.38333 |  |  | 0 |  | 0
Screens - Taxes > Dropdown Country | 0.35 | 0.75 | 1.25 | 0.76667 | 0 | 0.76667 | 0.38333 |  |  | 0 |  | 0
Screens - Transfer > Select location to send to | 0.75 | 1.25 | 2.75 | 1.4167 | 0 | 1.4167 | 0.70833 |  |  | 0 |  | 0
Screens - Transfer > Similar to cart, no totals | 0.75 | 1.25 | 2.75 | 1.4167 | 0 | 1.4167 | 0.70833 |  |  | 0 |  | 0
Scrum Reports | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Sharepoint Organization | 1 | 2 | 3 | 2 | 0 | 2 | 1 |  |  | 0 |  | 0
Status Meeting | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Team Meeting | 1 | 1.5 | 2.5 | 1.5833 | 0 | 1.5833 | 0.79167 |  |  | 0 |  | 0
Testing | 5 | 7.5 | 12.5 | 7.9167 | 0 | 7.9167 | 3.9583 |  |  | 0 |  | 0
WBS | 1 | 1.5 | 2 | 1.5 | 0 | 1.5 | 0.75 |  |  | 0 |  | 0
[10 empty] | 0 |  | 0
[5 empty] | Total Estimate | 153.3917 | 76.6958 |  | 0 | 0 | 0 | 0
[5 empty] | Time Budget | 0
[5 empty] | Slack Time | -153.3917 |  |  |  | 0 |  | 0

## Nathan
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration
Add Table - Accessories Table | 0.1 | 0.2 | 0.5
Add Table - Accounts Receivable Table | 0.1 | 0.2 | 0.5
Add Table - Brands Table | 0.1 | 0.2 | 0.5
Add Table - Clothing Table | 0.1 | 0.2 | 0.5
Add Table - Employees Table | 0.1 | 0.2 | 0.5
Add Table - Item Table to Club Table | 0.1 | 0.2 | 0.5
Add Table - Job Position Table | 0.1 | 0.2 | 0.5
Add Table - Layaway Table | 0.1 | 0.2 | 0.5
Add Table - Location Table | 0.1 | 0.2 | 0.5
Add Table - Model Table | 0.1 | 0.2 | 0.5
Add Table - On Hold Table | 0.1 | 0.2 | 0.5
Add Table - Orders Table | 0.1 | 0.2 | 0.5
Add Table - Returns Table | 0.1 | 0.2 | 0.5
Add Table - Tax Rate Table | 0.1 | 0.2 | 0.5
Add Table - Trade Ins Table | 0.1 | 0.2 | 0.5
Add Table - Transfers Table | 0.1 | 0.2 | 0.5
Add Table - User Info Table | 0.1 | 0.2 | 0.5
Change Requests | 1 | 1.5 | 3
Client Meetings | 5 | 8 | 16
Define Job Roles | 0.5 | 1 | 1.5
Estimates | 1 | 2.5 | 3
Final Report | 4 | 6 | 8
Functionality - Add Customer On Sale | 1.5 | 2.5 | 4
Functionality - Add Item to Sale | 1.5 | 2.5 | 4
Functionality - Adding used item, if < $300 remove PST | 0.5 | 1 | 1.5
Functionality - Bulk Load for Customers | 3 | 4 | 6
Functionality - Bulk Load for Employees | 3 | 4 | 6
Functionality - Bulk Load for Items | 3 | 4 | 6
Functionality - Cancel Sale | 1.5 | 2.5 | 4
Functionality - Checkout Calculate Balance | 0.5 | 1 | 1.5
Functionality - Checkout Calculate GST | 0.5 | 1 | 1.5
Functionality - Checkout Calculate On Sale Total | 0.5 | 1 | 1.5
Functionality - Checkout Calculate PST | 0.5 | 1 | 1.5
Functionality - Checkout Calculate Subtotal | 0.5 | 1 | 1.5
Functionality - Checkout Calculate Total Owing | 0.5 | 1 | 1.5
Functionality - Checkout Calculate Trade In Total | 0.5 | 1 | 1.5
Functionality - Create Employee Class | 3 | 5 | 7
Functionality - Create Threaded Current User Class | 3 | 5 | 8
Functionality - Dropdown for In Store Sale or Shipping | 1 | 1.5 | 3
Functionality - During Sale, all Header button disabled | 1 | 2 | 3
Functionality - Edit Customer | 1 | 1.5 | 2
Functionality - Edit Employee | 1 | 1.5 | 2
Functionality - Edit Item | 1 | 1.5 | 2
Functionality - From selected Customer, ability to Start Sale | 1 | 3 | 5
Functionality - Generic Trade In Sku | 2 | 3 | 5
Functionality - If Customer is Guest, no Layaway Option | 0.5 | 1 | 2
Functionality - Inventory Search | 0.5 | 1 | 1.5
Functionality - Inventory Search by Type | 1 | 1.5 | 3
Functionality - Make DLL more robust | 2 | 4 | 6
Functionality - Multi Threading for each Login | 2 | 4 | 8
Functionality - New Customer button | 1 | 1.5 | 2
Functionality - New Employee button | 1 | 1.5 | 2
Functionality - New Item button | 1 | 2 | 3
Functionality - Password only Login | 2 | 4 | 6
Functionality - Proceed To Checkout | 0.5 | 1 | 1.5
Functionality - Quick Sale, grab Guest Customer | 0.2 | 0.5 | 1
Functionality - Remove duplicate code in DLL | 1 | 2 | 4
Functionality - Remove Item From Cart | 1 | 1.5 | 2
Functionality - Roll Over Cost | 1 | 1.5 | 2
Functionality - Sale is processed, go home | 1 | 1.5 | 3
Functionality - Select Method of Payment, enter amount | 3 | 4.5 | 8
Functionality - Trade Ins (-) remove from Subtotal | 2 | 2.5 | 4
Functionality - Trade Ins Popup | 1 | 1.5 | 2
Functionality - Trade Ins see Cost not Price | 0.5 | 1.5 | 3
Learning current application | 10 | 15 | 20
Meeting Transciption | 2 | 2.5 | 4
Planning Meeting | 5 | 8 | 15
Project Proposal | 4 | 6 | 8
QA | 10 | 15 | 25
Research | 3 | 5 | 8
Review Transmittal Documentation | 2 | 4 | 6
Screens - Draw Sales Layout Designs | 2 | 2.5 | 3
Screens - Employees > more fields | 1 | 1.5 | 3
Screens - Initial Redesign | 1 | 3 | 4
Screens - Login at home page | 3 | 4 | 6
Screens - Master Page | 1.5 | 3 | 5
Screens - New Add Customer page | 1 | 1.5 | 2
Screens - New Add Employee page | 1 | 1.5 | 2
Screens - New Add Item page | 1 | 1.5 | 2
Screens - Reports > Cash Out | 0.5 | 1 | 1.5
Screens - Reports > Daily Sales | 0.5 | 1 | 1.5
Screens - Sales > Transfers | 0.5 | 1 | 3
Screens - Sales Cart | 2 | 3 | 5
Screens - Sales Checkout | 2 | 3 | 5
Screens - Settings > Bulk Excel Loads | 0.5 | 1 | 1.5
Screens - Settings > Employees | 0.5 | 1 | 1.5
Screens - Settings > Taxes | 0.5 | 1 | 1.5
Screens - Taxes > Dropdown Country | 0.5 | 1 | 1.5
Screens - Transfer > Select location to send to | 1 | 1.5 | 3
Screens - Transfer > Similar to cart, no totals | 1 | 1.5 | 3
Scrum Reports | 2 | 3 | 5
Sharepoint Organization | 2 | 4 | 6
Status Meeting | 2 | 3 | 5
Team Meeting | 2 | 3 | 5
Testing | 10 | 15 | 25
WBS | 2 | 3 | 4
| 143.9 | 233.4 | 374

## Tyler
Work Package | Optimistic Duration | Expected Duration | Pessimistic Duration
Add Table - Accessories Table | 0.5 | 1 | 3
Add Table - Accounts Receivable Table | 0.5 | 1 | 3
Add Table - Brands Table | 0.5 | 1 | 3
Add Table - Clothing Table | 0.5 | 1 | 3
Add Table - Employees Table | 0.5 | 1 | 3
Add Table - Item Table to Club Table
Add Table - Job Position Table | 0.5 | 1 | 3
Add Table - Layaway Table | 0.5 | 1 | 3
Add Table - Location Table | 0.5 | 1 | 3
Add Table - Model Table | 0.5 | 1 | 3
Add Table - On Hold Table | 0.5 | 1 | 3
Add Table - Orders Table | 0.5 | 1 | 3
Add Table - Returns Table | 0.5 | 1 | 3
Add Table - Tax Rate Table | 0.5 | 1 | 3
Add Table - Trade Ins Table | 0.5 | 1 | 3
Add Table - Transfers Table | 0.5 | 1 | 3
Add Table - User Info Table
Change Requests
Client Meetings
Define Job Roles | 0.2 | 0.5 | 1
Estimates
Final Report
Functionality - Add Customer On Sale
Functionality - Add Item to Sale
Functionality - Adding used item, if < $300 remove PST | 0.5 | 1.5 | 3
Functionality - Bulk Load for Customers
Functionality - Bulk Load for Employees
Functionality - Bulk Load for Items
Functionality - Cancel Sale
Functionality - Checkout Calculate Balance
Functionality - Checkout Calculate GST
Functionality - Checkout Calculate On Sale Total
Functionality - Checkout Calculate PST
Functionality - Checkout Calculate Subtotal
Functionality - Checkout Calculate Total Owing
Functionality - Checkout Calculate Trade In Total
Functionality - Create Employee Class | 2 | 3 | 5
Functionality - Create Threaded Current User Class
Functionality - Dropdown for In Store Sale or Shipping
Functionality - During Sale, all Header button disabled | 0.1 | 0.5 | 1
Functionality - Edit Customer
Functionality - Edit Employee
Functionality - Edit Item
Functionality - From selected Customer, ability to Start Sale | 0.5 | 1.5 | 4
Functionality - Generic Trade In Sku
Functionality - If Customer is Guest, no Layaway Option | 0.1 | 0.3 | 1.5
Functionality - Inventory Search
Functionality - Inventory Search by Type | 1 | 2 | 4
Functionality - Make DLL more robust
Functionality - Multi Threading for each Login | 3 | 6 | 9
Functionality - New Customer button
Functionality - New Employee button
Functionality - New Item button | 1 | 1.5 | 3
Functionality - Password only Login | 1 | 2 | 6
Functionality - Proceed To Checkout
Functionality - Quick Sale, grab Guest Customer | 0.5 | 1 | 3
Functionality - Remove duplicate code in DLL
Functionality - Remove Item From Cart
Functionality - Roll Over Cost
Functionality - Sale is processed, go home | 1 | 2 | 6
Functionality - Select Method of Payment, enter amount | 1 | 3 | 5
Functionality - Trade Ins (-) remove from Subtotal | 0.2 | 0.5 | 2
Functionality - Trade Ins Popup
Functionality - Trade Ins see Cost not Price
Learning current application
Meeting Transciption
Planning Meeting
Project Proposal
QA
Research
Review Transmittal Documentation
Screens - Draw Sales Layout Designs | 0.3 | 1 | 1.5
Screens - Employees > more fields | 1 | 2 | 3
Screens - Initial Redesign
Screens - Login at home page | 1 | 2 | 6
Screens - Master Page
Screens - New Add Customer page
Screens - New Add Employee page
Screens - New Add Item page
Screens - Reports > Cash Out | 1 | 2 | 3
Screens - Reports > Daily Sales | 1 | 1.5 | 2.5
Screens - Sales > Transfers | 0.5 | 1 | 2.5
Screens - Sales Cart
Screens - Sales Checkout
Screens - Settings > Bulk Excel Loads | 3 | 4 | 6
Screens - Settings > Employees | 0.2 | 0.5 | 1
Screens - Settings > Taxes | 0.2 | 0.5 | 1
Screens - Taxes > Dropdown Country | 0.2 | 0.5 | 1
Screens - Transfer > Select location to send to | 0.5 | 1 | 2.5
Screens - Transfer > Similar to cart, no totals | 0.5 | 1 | 2.5
Scrum Reports
Sharepoint Organization
Status Meeting
Team Meeting
Testing
WBS
| 29 | 57.3 | 131