## Sheet1
TEAM SCRUM MEETING
Attendees: |  | Nathan | Date: | Wed Mar 22
|  |  | Time: | 9:40
Rincy
Franko
MINUTES
Agenda Item: | Team Building
Presenter: | Franko
Discussion: | Where to meet and what time?
Conclusion: | We will meet at Famoso downtown @ 5 pm for supper. After supper we will head over to Escape Manor to participate in an Escape room. This should take until around 8. Then head home.
Agenda Item: | Project Proposal
Presenter: | Rincy
Discussion: | The Project Proposal will need to be completed by 4/3 for BCOM class.
Conclusion: | Rincy will provide a copy of the proposal guidelines so that we can make sure we hit all the proper points. It will need to be between 8-12 pages long.
Agenda Item: | Continue to Review application
Presenter: | Nathan
Discussion: | Continue to look through application and become familiar with it.
Conclusion: | A couple points to note will be that at this point the DLL is not getting updated the way it should after it is built. If we can figure this out/correct it then we will have full control over the current model.
Agenda Item: | Change the format to MVC
Presenter: | Nathan
Discussion: | We asked Gavin if it would be possible to move the site to MVC format.
Conclusion: | He advised that as long as we include as part of the project plan that there would be no problem with it. This will make it easier to manage the site and make it far more easier to work with.
Agenda Item: | Meting with Carlo
Presenter: | Nathan
Discussion: | We will be meeting again with Carlo on 3/28.
Conclusion: | At this point we will go through the current application and how it is working. What he likes, doesn't like, and anything that is missing. At this point we will sell him on updating the tables to make the database more dynamic and planning for the future.